## Project_Master
Project_ID | Project_Name | Client | Project_Manager | Total_Budget | Priority | Project_Status | Primary_Technology | Start_Date | End_Date
P001 | Enterprise Project 1 | Client 1 | Neeraj | 850487 | High | Active | Power BI | 2026-03-01 | 2026-05-01
P002 | Enterprise Project 2 | Client 2 | Bharat | 296739 | Medium | Completed | Three.js | 2026-03-02 | 2026-05-02
P003 | Enterprise Project 3 | Client 3 | Rahul | 206225 | Low | On Hold | NET | 2026-03-03 | 2026-05-03
P004 | Enterprise Project 4 | Client 4 | Ankit | 957572 | High | Not Started | Angular | 2026-03-04 | 2026-05-04
P005 | Enterprise Project 5 | Client 5 | Vivek | 468389 | Medium | Active | Node.js | 2026-03-05 | 2026-05-05
P006 | Enterprise Project 6 | Client 6 | Mohit | 436787 | Low | Completed | React | 2026-03-06 | 2026-05-06
P007 | Enterprise Project 7 | Client 7 | Sahil | 414053 | High | On Hold | Power BI | 2026-03-07 | 2026-05-07
P008 | Enterprise Project 8 | Client 8 | Harsh | 326316 | Medium | Not Started | Three.js | 2026-03-08 | 2026-05-08
P009 | Enterprise Project 9 | Client 9 | Kunal | 952246 | Low | Active | NET | 2026-03-09 | 2026-05-09
P010 | Enterprise Project 10 | Client 10 | Neeraj | 287473 | High | Completed | Angular | 2026-03-10 | 2026-05-10
P011 | Enterprise Project 11 | Client 11 | Bharat | 889570 | Medium | On Hold | Node.js | 2026-03-11 | 2026-05-11
P012 | Enterprise Project 12 | Client 12 | Rahul | 956646 | Low | Not Started | React | 2026-03-12 | 2026-05-12
P013 | Enterprise Project 13 | Client 13 | Ankit | 1115518 | High | Active | Power BI | 2026-03-13 | 2026-05-13
P014 | Enterprise Project 14 | Client 14 | Vivek | 751858 | Medium | Completed | Three.js | 2026-03-14 | 2026-05-14

## Milestones
Milestone_ID | Project_ID | Milestone_Name | Milestone_Order | Milestone_Budget | Planned_Date | Completion_Date | Milestone_Status
MS001 | P001 | Requirement Signoff | 1 | 160604 | 2026-03-11 |  | Pending
MS002 | P001 | Core Features | 2 | 74561 | 2026-03-19 |  | In Progress
MS003 | P001 | Requirement Signoff | 3 | 207815 | 2026-03-28 | 2026-03-28 | Completed
MS004 | P002 | Requirement Signoff | 1 | 102124 | 2026-03-12 |  | Pending
MS005 | P002 | Testing | 2 | 107787 | 2026-03-24 |  | In Progress
MS006 | P002 | Core Features | 3 | 248916 | 2026-03-31 | 2026-04-01 | Completed
MS007 | P003 | Deployment | 1 | 160785 | 2026-03-14 |  | Pending
MS008 | P003 | Integration | 2 | 90758 | 2026-03-23 |  | In Progress
MS009 | P003 | Core Features | 3 | 74312 | 2026-03-30 | 2026-04-01 | Completed
MS010 | P004 | Core Features | 1 | 144104 | 2026-03-17 |  | Pending
MS011 | P004 | Requirement Signoff | 2 | 119342 | 2026-03-24 |  | In Progress
MS012 | P004 | Requirement Signoff | 3 | 82722 | 2026-03-30 | 2026-04-03 | Completed
MS013 | P005 | Core Features | 1 | 194714 | 2026-03-18 |  | Pending
MS014 | P005 | Deployment | 2 | 212141 | 2026-03-25 |  | In Progress
MS015 | P005 | Deployment | 3 | 68233 | 2026-04-02 | 2026-04-02 | Completed
MS016 | P006 | Deployment | 1 | 109742 | 2026-03-16 |  | Pending
MS017 | P006 | Core Features | 2 | 274216 | 2026-03-26 |  | In Progress
MS018 | P007 | Core Features | 1 | 149647 | 2026-03-18 |  | In Progress
MS019 | P007 | Deployment | 2 | 268657 | 2026-03-27 | 2026-03-31 | Completed
MS020 | P008 | Integration | 1 | 143132 | 2026-03-20 | 2026-03-19 | Completed
MS021 | P008 | Deployment | 2 | 119986 | 2026-03-27 |  | Pending
MS022 | P009 | Requirement Signoff | 1 | 216455 | 2026-03-19 |  | Pending
MS023 | P009 | Requirement Signoff | 2 | 241136 | 2026-03-28 |  | In Progress
MS024 | P009 | Testing | 3 | 149471 | 2026-04-05 | 2026-04-04 | Completed
MS025 | P009 | Deployment | 4 | 230397 | 2026-04-14 |  | Pending
MS026 | P010 | Deployment | 1 | 135008 | 2026-03-24 | 2026-03-24 | Completed
MS027 | P010 | Final Delivery | 2 | 265430 | 2026-03-28 |  | Pending
MS028 | P010 | Integration | 3 | 155162 | 2026-04-05 |  | In Progress
MS029 | P010 | Final Delivery | 4 | 289373 | 2026-04-15 | 2026-04-13 | Completed
MS030 | P011 | Deployment | 1 | 132490 | 2026-03-25 |  | In Progress
MS031 | P011 | Testing | 2 | 281914 | 2026-03-30 | 2026-04-03 | Completed
MS032 | P011 | Final Delivery | 3 | 119436 | 2026-04-09 |  | Pending
MS033 | P012 | Final Delivery | 1 | 245294 | 2026-03-23 |  | In Progress
MS034 | P012 | Deployment | 2 | 203245 | 2026-04-03 | 2026-04-04 | Completed
MS035 | P012 | Requirement Signoff | 3 | 154700 | 2026-04-10 |  | Pending
MS036 | P012 | Final Delivery | 4 | 86262 | 2026-04-17 |  | In Progress
MS037 | P013 | Testing | 1 | 73831 | 2026-03-27 |  | Pending
MS038 | P013 | Core Features | 2 | 90066 | 2026-03-31 |  | In Progress
MS039 | P013 | Requirement Signoff | 3 | 66653 | 2026-04-09 | 2026-04-12 | Completed
MS040 | P013 | Testing | 4 | 206208 | 2026-04-19 |  | Pending
MS041 | P014 | Requirement Signoff | 1 | 275648 | 2026-03-27 | 2026-03-28 | Completed
MS042 | P014 | Deployment | 2 | 238932 | 2026-04-01 |  | Pending
MS043 | P014 | Deployment | 3 | 281941 | 2026-04-09 |  | In Progress

## Modules
Module_ID | Milestone_ID | Module_Name | Module_Order | Resources
M001 | MS001 | Backend | 1 | Unreal_Artist, Dev_C, 3D_Team, Dev_A
M002 | MS001 | Dashboard | 2 | Dev_B, QA_Team, Dev_A
M003 | MS002 | 3D Scene | 1 | Dev_C, DB_Admin, Dev_B, Dev_A
M004 | MS002 | Auth | 2 | Dev_C, 3D_Team, DB_Admin, Dev_B
M005 | MS003 | 3D Scene | 1 | Unreal_Artist, Dev_B, DB_Admin
M006 | MS003 | API | 2 | Dev_A, DB_Admin, Dev_C, QA_Team
M007 | MS004 | Auth | 1 | Dev_C, Unreal_Artist
M008 | MS004 | API | 2 | Dev_B, DB_Admin
M009 | MS005 | 3D Scene | 1 | 3D_Team, QA_Team
M010 | MS005 | 3D Scene | 2 | Unreal_Artist, DB_Admin
M011 | MS006 | Payment | 1 | Dev_B, 3D_Team
M012 | MS006 | Auth | 2 | Dev_B, Dev_C, DB_Admin, QA_Team
M013 | MS007 | Payment | 1 | Unreal_Artist, 3D_Team, Dev_B, Dev_C
M014 | MS007 | API | 2 | 3D_Team, Dev_C, QA_Team, DB_Admin
M015 | MS008 | Backend | 1 | Dev_B, Dev_A
M016 | MS008 | Auth | 2 | DB_Admin, Unreal_Artist
M017 | MS009 | Auth | 1 | Dev_B, Dev_A, 3D_Team, DB_Admin
M018 | MS009 | API | 2 | Dev_A, Dev_C
M019 | MS010 | Database | 1 | Dev_B, Dev_C, QA_Team, Unreal_Artist
M020 | MS010 | Database | 2 | 3D_Team, DB_Admin
M021 | MS011 | Auth | 1 | Dev_B, QA_Team, 3D_Team
M022 | MS011 | Payment | 2 | Dev_A, 3D_Team
M023 | MS012 | 3D Scene | 1 | QA_Team, Unreal_Artist, 3D_Team
M024 | MS012 | Payment | 2 | Dev_A, 3D_Team, Unreal_Artist, DB_Admin
M025 | MS013 | Auth | 1 | Dev_C, Dev_A, Dev_B, DB_Admin
M026 | MS013 | Backend | 2 | QA_Team, Dev_B, Unreal_Artist, 3D_Team
M027 | MS014 | 3D Scene | 1 | Dev_B, Dev_A, QA_Team
M028 | MS014 | API | 2 | Dev_A, Unreal_Artist, DB_Admin, 3D_Team
M029 | MS015 | Payment | 1 | Dev_B, QA_Team
M030 | MS015 | Auth | 2 | Dev_B, QA_Team, Dev_A
M031 | MS016 | 3D Scene | 1 | Dev_A, QA_Team, Dev_C
M032 | MS016 | Dashboard | 2 | Dev_C, QA_Team, DB_Admin
M033 | MS017 | Auth | 1 | QA_Team, Dev_B, 3D_Team, Dev_C
M034 | MS017 | Database | 2 | DB_Admin, 3D_Team
M035 | MS018 | API | 1 | 3D_Team, Dev_C
M036 | MS018 | Database | 2 | DB_Admin, QA_Team
M037 | MS019 | 3D Scene | 1 | Dev_B, Dev_A, DB_Admin, 3D_Team
M038 | MS019 | API | 2 | Dev_A, DB_Admin
M039 | MS020 | Database | 1 | Unreal_Artist, Dev_B, QA_Team, Dev_A
M040 | MS020 | API | 2 | DB_Admin, Unreal_Artist
M041 | MS021 | Backend | 1 | Dev_A, QA_Team, DB_Admin, Dev_C
M042 | MS021 | Backend | 2 | 3D_Team, Unreal_Artist
M043 | MS022 | Auth | 1 | Dev_C, QA_Team
M044 | MS022 | 3D Scene | 2 | 3D_Team, Dev_C, QA_Team, Unreal_Artist
M045 | MS023 | Database | 1 | Dev_A, QA_Team
M046 | MS023 | Database | 2 | Dev_A, Unreal_Artist, DB_Admin, Dev_B
M047 | MS024 | Auth | 1 | Dev_B, Dev_C, Dev_A
M048 | MS024 | 3D Scene | 2 | Dev_C, Dev_B, QA_Team
M049 | MS025 | Dashboard | 1 | 3D_Team, Dev_C, DB_Admin, Dev_A
M050 | MS025 | Backend | 2 | Dev_C, 3D_Team, Dev_A, Dev_B
M051 | MS026 | Database | 1 | Dev_A, 3D_Team
M052 | MS026 | Database | 2 | Dev_C, Unreal_Artist
M053 | MS027 | Auth | 1 | 3D_Team, Dev_C
M054 | MS027 | Backend | 2 | 3D_Team, Dev_C, DB_Admin, QA_Team
M055 | MS028 | Payment | 1 | Dev_A, 3D_Team
M056 | MS028 | 3D Scene | 2 | Dev_A, Unreal_Artist, Dev_C
M057 | MS029 | Auth | 1 | 3D_Team, Dev_C
M058 | MS029 | API | 2 | QA_Team, DB_Admin, Unreal_Artist, Dev_A
M059 | MS030 | Database | 1 | 3D_Team, Dev_B
M060 | MS030 | Database | 2 | Unreal_Artist, Dev_C
M061 | MS031 | Backend | 1 | Dev_B, QA_Team, Unreal_Artist, Dev_A
M062 | MS031 | Auth | 2 | Unreal_Artist, Dev_A, Dev_C
M063 | MS032 | 3D Scene | 1 | Dev_B, 3D_Team, Dev_A, Dev_C
M064 | MS032 | Auth | 2 | Unreal_Artist, QA_Team, DB_Admin, Dev_B
M065 | MS033 | Payment | 1 | Unreal_Artist, Dev_B
M066 | MS033 | Backend | 2 | Dev_B, 3D_Team
M067 | MS034 | Backend | 1 | Unreal_Artist, 3D_Team, Dev_B
M068 | MS034 | API | 2 | Unreal_Artist, 3D_Team
M069 | MS035 | Auth | 1 | Unreal_Artist, Dev_A, QA_Team
M070 | MS035 | Backend | 2 | Unreal_Artist, QA_Team
M071 | MS036 | API | 1 | Unreal_Artist, Dev_B, 3D_Team
M072 | MS037 | 3D Scene | 1 | Dev_B, QA_Team, Dev_C, DB_Admin
M073 | MS038 | Backend | 1 | Unreal_Artist, Dev_C
M074 | MS039 | API | 1 | DB_Admin, QA_Team, Unreal_Artist, Dev_C
M075 | MS040 | Database | 1 | Dev_C, Dev_B
M076 | MS041 | Payment | 1 | Dev_A, Unreal_Artist, DB_Admin
M077 | MS042 | Database | 1 | 3D_Team, Dev_C, QA_Team
M078 | MS043 | Backend | 1 | Dev_A, QA_Team, DB_Admin, Dev_B

## Issue_Log
Issue_ID | Milestone_ID | Reported_Date | Reported_By | Description | Impact | Status | Issue_Source | Root_Cause | Final_Solution | Target_Resolution_Date | Resolved_Date
I001 | MS008 | 2026-03-02 | Kunal | Operational issue encountered | High | Resolved | Development Team | Resource shortage | API patch applied | 2026-03-31 | 2026-03-03
I002 | MS015 | 2026-03-31 | Mohit | Operational issue encountered | Medium | Closed | Client | Resource shortage | Additional resources assigned | 2026-04-30 | 2026-04-07
I003 | MS022 | 2026-03-30 | Mohit | Operational issue encountered | High | Open | Client | Resource shortage | Timeline revised | 2026-04-16
I004 | MS029 | 2026-03-29 | Vivek | Operational issue encountered | High | In Progress | Management | Client delay | Timeline revised | 2026-04-14
I005 | MS036 | 2026-03-13 | Rahul | Operational issue encountered | Low | Resolved | Management | Resource shortage | Requirement clarified | 2026-04-11 | 2026-03-31
I006 | MS043 | 2026-03-31 | Vivek | Operational issue encountered | Medium | Closed | Development Team | API failure | Additional resources assigned | 2026-04-19 | 2026-04-06
I007 | MS007 | 2026-03-10 | Sahil | Operational issue encountered | High | Open | Development Team | Resource shortage | Data corrected | 2026-03-26
I008 | MS014 | 2026-03-11 | Harsh | Operational issue encountered | High | In Progress | Client | Requirement gap | API patch applied | 2026-04-01
I009 | MS021 | 2026-03-16 | Vivek | Operational issue encountered | High | Resolved | Development Team | Resource shortage | Data corrected | 2026-04-15 | 2026-03-19
I010 | MS028 | 2026-03-20 | Vivek | Operational issue encountered | Low | Closed | Client | Data mismatch | Server upgraded | 2026-04-06 | 2026-03-28
I011 | MS035 | 2026-03-01 | Harsh | Operational issue encountered | High | Open | Client | Server outage | Data corrected | 2026-03-09
I012 | MS042 | 2026-03-14 | Ankit | Operational issue encountered | High | In Progress | Development Team | Server outage | Timeline revised | 2026-04-10
I013 | MS006 | 2026-03-16 | Neeraj | Operational issue encountered | Low | Resolved | Management | Data mismatch | Data corrected | 2026-04-04 | 2026-03-21
I014 | MS013 | 2026-03-06 | Neeraj | Operational issue encountered | High | Closed | Client | API failure | Timeline revised | 2026-04-04 | 2026-03-21
I015 | MS020 | 2026-03-15 | Kunal | Operational issue encountered | High | Open | Development Team | Client delay | API patch applied | 2026-03-26
I016 | MS027 | 2026-03-31 | Kunal | Operational issue encountered | Medium | In Progress | Development Team | Server outage | Timeline revised | 2026-04-21
I017 | MS034 | 2026-03-29 | Harsh | Operational issue encountered | Medium | Resolved | Client | Resource shortage | Additional resources assigned | 2026-04-10 | 2026-04-14
I018 | MS041 | 2026-03-09 | Vivek | Operational issue encountered | Medium | Closed | Client | Resource shortage | API patch applied | 2026-04-01 | 2026-03-17
I019 | MS005 | 2026-03-10 | Mohit | Operational issue encountered | Medium | Open | Development Team | API failure | Requirement clarified | 2026-03-24
I020 | MS012 | 2026-03-05 | Sahil | Operational issue encountered | High | In Progress | Client | Resource shortage | Data corrected | 2026-03-16
I021 | MS019 | 2026-03-07 | Mohit | Operational issue encountered | High | Resolved | Management | Server outage | API patch applied | 2026-03-16 | 2026-03-21
I022 | MS026 | 2026-03-02 | Neeraj | Operational issue encountered | High | Closed | Management | Server outage | API patch applied | 2026-03-15 | 2026-03-15
I023 | MS033 | 2026-03-01 | Sahil | Operational issue encountered | Medium | Open | Development Team | Resource shortage | Requirement clarified | 2026-03-19
I024 | MS040 | 2026-03-24 | Ankit | Operational issue encountered | Medium | In Progress | Client | Client delay | Timeline revised | 2026-04-17
I025 | MS004 | 2026-03-14 | Mohit | Operational issue encountered | High | Resolved | Development Team | Server outage | Server upgraded | 2026-04-05 | 2026-03-27
I026 | MS011 | 2026-03-24 | Kunal | Operational issue encountered | Low | Closed | Management | Requirement gap | API patch applied | 2026-04-05 | 2026-03-29
I027 | MS018 | 2026-03-19 | Bharat | Operational issue encountered | High | Open | Management | Data mismatch | Server upgraded | 2026-04-16
I028 | MS025 | 2026-03-28 | Neeraj | Operational issue encountered | Medium | In Progress | Management | Client delay | Data corrected | 2026-04-18
I029 | MS032 | 2026-03-07 | Sahil | Operational issue encountered | Medium | Resolved | Management | Client delay | Requirement clarified | 2026-03-28 | 2026-03-18
I030 | MS039 | 2026-03-27 | Kunal | Operational issue encountered | Low | Closed | Management | Data mismatch | API patch applied | 2026-04-05 | 2026-03-28
I031 | MS003 | 2026-03-21 | Neeraj | Operational issue encountered | Low | Open | Client | Data mismatch | Additional resources assigned | 2026-03-30
I032 | MS010 | 2026-03-27 | Rahul | Operational issue encountered | Low | In Progress | Client | Server outage | Timeline revised | 2026-04-03
I033 | MS017 | 2026-03-22 | Harsh | Operational issue encountered | High | Resolved | Management | Client delay | Timeline revised | 2026-04-01 | 2026-03-29
I034 | MS024 | 2026-03-06 | Rahul | Operational issue encountered | Medium | Closed | Client | Requirement gap | Timeline revised | 2026-04-01 | 2026-03-10
I035 | MS031 | 2026-03-01 | Sahil | Operational issue encountered | Medium | Open | Development Team | Data mismatch | Timeline revised | 2026-03-17
I036 | MS038 | 2026-03-03 | Ankit | Operational issue encountered | Low | In Progress | Development Team | Client delay | Additional resources assigned | 2026-03-28
I037 | MS002 | 2026-03-28 | Neeraj | Operational issue encountered | Medium | Resolved | Development Team | Server outage | Timeline revised | 2026-04-25 | 2026-04-01
I038 | MS009 | 2026-03-22 | Mohit | Operational issue encountered | Low | Closed | Management | Server outage | Server upgraded | 2026-04-09 | 2026-04-08
I039 | MS016 | 2026-03-04 | Harsh | Operational issue encountered | High | Open | Client | Server outage | Requirement clarified | 2026-03-24
I040 | MS023 | 2026-03-06 | Vivek | Operational issue encountered | High | In Progress | Development Team | Server outage | Timeline revised | 2026-04-05
I041 | MS030 | 2026-03-15 | Mohit | Operational issue encountered | Low | Resolved | Client | Client delay | Additional resources assigned | 2026-04-04 | 2026-03-24
I042 | MS037 | 2026-03-29 | Sahil | Operational issue encountered | Medium | Closed | Client | Server outage | Data corrected | 2026-04-19 | 2026-04-13
I043 | MS001 | 2026-03-28 | Harsh | Operational issue encountered | Low | Open | Management | Client delay | Data corrected | 2026-04-14
I044 | MS008 | 2026-03-11 | Vivek | Operational issue encountered | High | In Progress | Client | Requirement gap | Timeline revised | 2026-03-26
I045 | MS015 | 2026-03-31 | Sahil | Operational issue encountered | Medium | Resolved | Development Team | Data mismatch | Server upgraded | 2026-04-13 | 2026-04-08
I046 | MS022 | 2026-03-23 | Harsh | Operational issue encountered | Low | Closed | Client | Client delay | Additional resources assigned | 2026-04-14 | 2026-04-08
I047 | MS029 | 2026-03-08 | Ankit | Operational issue encountered | Medium | Open | Development Team | Requirement gap | Additional resources assigned | 2026-03-27
I048 | MS036 | 2026-03-12 | Kunal | Operational issue encountered | Medium | In Progress | Management | Resource shortage | Timeline revised | 2026-04-03
I049 | MS043 | 2026-03-18 | Vivek | Operational issue encountered | Medium | Resolved | Management | Data mismatch | Requirement clarified | 2026-04-04 | 2026-04-02
I050 | MS007 | 2026-03-04 | Bharat | Operational issue encountered | High | Closed | Development Team | Resource shortage | Data corrected | 2026-04-03 | 2026-03-15
I051 | MS014 | 2026-03-06 | Harsh | Operational issue encountered | Medium | Open | Development Team | Requirement gap | Data corrected | 2026-03-19
I052 | MS021 | 2026-03-25 | Vivek | Operational issue encountered | Low | In Progress | Client | Client delay | Timeline revised | 2026-04-17
I053 | MS028 | 2026-03-08 | Neeraj | Operational issue encountered | High | Resolved | Development Team | Data mismatch | Data corrected | 2026-03-26 | 2026-03-18
I054 | MS035 | 2026-03-09 | Vivek | Operational issue encountered | High | Closed | Client | Resource shortage | Server upgraded | 2026-03-17 | 2026-03-27
I055 | MS042 | 2026-03-28 | Neeraj | Operational issue encountered | High | Open | Management | Server outage | Server upgraded | 2026-04-19
I056 | MS006 | 2026-03-16 | Rahul | Operational issue encountered | Low | In Progress | Management | Server outage | Requirement clarified | 2026-04-06
I057 | MS013 | 2026-03-04 | Bharat | Operational issue encountered | High | Resolved | Development Team | Resource shortage | API patch applied | 2026-03-13 | 2026-03-20
I058 | MS020 | 2026-03-02 | Bharat | Operational issue encountered | Low | Closed | Client | Requirement gap | Data corrected | 2026-03-13 | 2026-03-12
I059 | MS027 | 2026-03-25 | Ankit | Operational issue encountered | High | Open | Management | Server outage | Timeline revised | 2026-04-14
I060 | MS034 | 2026-03-30 | Sahil | Operational issue encountered | Medium | In Progress | Development Team | Requirement gap | Requirement clarified | 2026-04-20
I061 | MS041 | 2026-03-02 | Ankit | Operational issue encountered | High | Resolved | Client | Client delay | Additional resources assigned | 2026-03-28 | 2026-03-06
I062 | MS005 | 2026-03-22 | Rahul | Operational issue encountered | High | Closed | Client | Data mismatch | Data corrected | 2026-03-31 | 2026-03-30
I063 | MS012 | 2026-03-01 | Harsh | Operational issue encountered | Medium | Open | Client | Data mismatch | API patch applied | 2026-03-21
I064 | MS019 | 2026-03-10 | Harsh | Operational issue encountered | Low | In Progress | Development Team | Data mismatch | Requirement clarified | 2026-04-08

## Daily_Activity
Date | Status | Remark | Updated_On | Module_ID | Step_Name
2026-04-29 | Blocked | Task completed | 2026-04-29 | M007 | Requirement Signoff
2026-03-28 | Completed | Task completed | 2026-03-28 | M030 | Deployment
2026-04-11 | Not Started | Dependency pending | 2026-04-11 | M051 | Deployment
2026-04-22 | Not Started | Issue investigation | 2026-04-22 | M072 | Testing
2026-03-04 | Not Started | Dependency pending | 2026-03-04 | M009 | Testing
2026-04-08 | On Hold | Dependency pending | 2026-04-08 | M032 | Deployment
2026-03-29 | Completed | Testing ongoing | 2026-03-29 | M053 | Final Delivery
2026-04-14 | Blocked | Code review ongoing | 2026-04-14 | M073 | Core Features
2026-04-30 | Blocked | Testing ongoing | 2026-04-30 | M011 | Core Features
2026-03-29 | Completed | Client feedback applied | 2026-03-29 | M034 | Core Features
2026-04-26 | In Progress | Initial development | 2026-04-26 | M055 | Integration
2026-04-08 | Blocked | Client feedback applied | 2026-04-08 | M074 | Requirement Signoff
2026-03-06 | Not Started | Client feedback applied | 2026-03-06 | M013 | Deployment
2026-04-18 | Blocked | Client feedback applied | 2026-04-18 | M036 | Core Features
2026-04-18 | Not Started | Testing ongoing | 2026-04-18 | M057 | Final Delivery
2026-04-03 | In Progress | Dependency pending | 2026-04-03 | M075 | Testing
2026-03-12 | On Hold | Code review ongoing | 2026-03-12 | M015 | Integration
2026-04-10 | In Progress | Issue investigation | 2026-04-10 | M038 | Deployment
2026-03-31 | Blocked | Code review ongoing | 2026-03-31 | M059 | Deployment
2026-03-22 | Blocked | Issue investigation | 2026-03-22 | M076 | Requirement Signoff
2026-04-24 | Not Started | Initial development | 2026-04-24 | M017 | Core Features
2026-03-27 | In Progress | Dependency pending | 2026-03-27 | M040 | Integration
2026-04-12 | In Progress | Client feedback applied | 2026-04-12 | M061 | Testing
2026-03-30 | Completed | Initial development | 2026-03-30 | M077 | Deployment
2026-03-17 | Blocked | Issue investigation | 2026-03-17 | M019 | Core Features
2026-04-19 | In Progress | Client feedback applied | 2026-04-19 | M042 | Deployment
2026-04-12 | On Hold | Testing ongoing | 2026-04-12 | M063 | Final Delivery
2026-03-27 | Completed | Task completed | 2026-03-27 | M078 | Deployment
2026-04-03 | Blocked | Testing ongoing | 2026-04-03 | M021 | Requirement Signoff
2026-04-10 | In Progress | Client feedback applied | 2026-04-10 | M044 | Requirement Signoff
2026-03-14 | Blocked | Deployment prep | 2026-03-14 | M065 | Final Delivery
2026-04-29 | Blocked | Testing ongoing | 2026-04-29 | M002 | Requirement Signoff
2026-04-26 | In Progress | Issue investigation | 2026-04-26 | M023 | Requirement Signoff
2026-03-02 | On Hold | Task completed | 2026-03-02 | M046 | Requirement Signoff
2026-04-15 | Not Started | Dependency pending | 2026-04-15 | M067 | Deployment
2026-04-05 | Completed | Code review ongoing | 2026-04-05 | M004 | Core Features
2026-03-06 | Not Started | Issue investigation | 2026-03-06 | M025 | Core Features
2026-03-30 | Completed | Deployment prep | 2026-03-30 | M048 | Testing
2026-04-01 | Blocked | Dependency pending | 2026-04-01 | M069 | Requirement Signoff
2026-03-27 | In Progress | Testing ongoing | 2026-03-27 | M006 | Requirement Signoff
2026-03-16 | In Progress | Deployment prep | 2026-03-16 | M027 | Deployment
2026-03-25 | Not Started | Deployment prep | 2026-03-25 | M050 | Deployment
2026-04-25 | Completed | Dependency pending | 2026-04-25 | M071 | Final Delivery
2026-04-19 | In Progress | Initial development | 2026-04-19 | M008 | Requirement Signoff
2026-04-29 | On Hold | Dependency pending | 2026-04-29 | M029 | Deployment
2026-04-22 | Completed | Dependency pending | 2026-04-22 | M052 | Deployment
2026-04-16 | Blocked | Testing ongoing | 2026-04-16 | M072 | Testing
2026-04-25 | Not Started | Testing ongoing | 2026-04-25 | M010 | Testing
2026-04-04 | In Progress | Initial development | 2026-04-04 | M031 | Deployment
2026-03-22 | On Hold | Code review ongoing | 2026-03-22 | M054 | Final Delivery
2026-03-30 | Blocked | Task completed | 2026-03-30 | M073 | Core Features
2026-04-14 | Not Started | Code review ongoing | 2026-04-14 | M012 | Core Features
2026-03-15 | In Progress | Client feedback applied | 2026-03-15 | M033 | Core Features
2026-03-21 | In Progress | Code review ongoing | 2026-03-21 | M056 | Integration
2026-03-25 | Not Started | Testing ongoing | 2026-03-25 | M074 | Requirement Signoff
2026-03-03 | Not Started | Initial development | 2026-03-03 | M014 | Deployment
2026-04-25 | Completed | Testing ongoing | 2026-04-25 | M035 | Core Features
2026-03-07 | On Hold | Testing ongoing | 2026-03-07 | M058 | Final Delivery
2026-03-01 | Not Started | Code review ongoing | 2026-03-01 | M075 | Testing
2026-04-25 | Not Started | Issue investigation | 2026-04-25 | M016 | Integration
2026-03-31 | Blocked | Initial development | 2026-03-31 | M037 | Deployment
2026-04-09 | In Progress | Issue investigation | 2026-04-09 | M060 | Deployment
2026-04-24 | Blocked | Code review ongoing | 2026-04-24 | M076 | Requirement Signoff
2026-03-21 | In Progress | Client feedback applied | 2026-03-21 | M018 | Core Features
2026-04-09 | Completed | Task completed | 2026-04-09 | M039 | Integration
2026-04-10 | Blocked | Task completed | 2026-04-10 | M062 | Testing
2026-04-17 | Completed | Code review ongoing | 2026-04-17 | M077 | Deployment
2026-03-07 | Completed | Testing ongoing | 2026-03-07 | M020 | Core Features
2026-03-11 | Blocked | Client feedback applied | 2026-03-11 | M041 | Deployment
2026-03-03 | Blocked | Client feedback applied | 2026-03-03 | M064 | Final Delivery
2026-03-19 | Blocked | Initial development | 2026-03-19 | M078 | Deployment
2026-03-28 | Not Started | Task completed | 2026-03-28 | M022 | Requirement Signoff
2026-04-03 | In Progress | Deployment prep | 2026-04-03 | M043 | Requirement Signoff
2026-03-11 | Not Started | Issue investigation | 2026-03-11 | M066 | Final Delivery
2026-04-09 | In Progress | Task completed | 2026-04-09 | M001 | Requirement Signoff
2026-04-01 | On Hold | Deployment prep | 2026-04-01 | M024 | Requirement Signoff
2026-03-15 | In Progress | Dependency pending | 2026-03-15 | M045 | Requirement Signoff
2026-03-30 | Blocked | Client feedback applied | 2026-03-30 | M068 | Deployment
2026-04-27 | In Progress | Dependency pending | 2026-04-27 | M003 | Core Features
2026-04-13 | On Hold | Deployment prep | 2026-04-13 | M026 | Core Features
2026-03-05 | In Progress | Initial development | 2026-03-05 | M047 | Testing
2026-04-07 | Blocked | Code review ongoing | 2026-04-07 | M070 | Requirement Signoff
2026-04-14 | Blocked | Testing ongoing | 2026-04-14 | M005 | Requirement Signoff
2026-04-24 | Blocked | Task completed | 2026-04-24 | M028 | Deployment
2026-03-25 | In Progress | Issue investigation | 2026-03-25 | M049 | Deployment
2026-03-16 | In Progress | Initial development | 2026-03-16 | M071 | Final Delivery
2026-04-06 | Blocked | Dependency pending | 2026-04-06 | M007 | Requirement Signoff
2026-03-02 | In Progress | Dependency pending | 2026-03-02 | M030 | Deployment
2026-03-01 | On Hold | Client feedback applied | 2026-03-01 | M051 | Deployment
2026-04-28 | On Hold | Testing ongoing | 2026-04-28 | M072 | Testing
2026-04-23 | Blocked | Task completed | 2026-04-23 | M009 | Testing
2026-04-08 | Blocked | Task completed | 2026-04-08 | M032 | Deployment
2026-04-10 | Not Started | Dependency pending | 2026-04-10 | M053 | Final Delivery
2026-04-13 | Not Started | Issue investigation | 2026-04-13 | M073 | Core Features
2026-04-27 | Completed | Dependency pending | 2026-04-27 | M011 | Core Features
2026-04-20 | In Progress | Client feedback applied | 2026-04-20 | M034 | Core Features
2026-04-07 | Blocked | Deployment prep | 2026-04-07 | M055 | Integration
2026-03-06 | Blocked | Initial development | 2026-03-06 | M074 | Requirement Signoff
2026-04-17 | In Progress | Deployment prep | 2026-04-17 | M013 | Deployment
2026-03-13 | Not Started | Initial development | 2026-03-13 | M036 | Core Features
2026-04-03 | On Hold | Dependency pending | 2026-04-03 | M057 | Final Delivery
2026-04-23 | Not Started | Dependency pending | 2026-04-23 | M075 | Testing
2026-04-28 | In Progress | Dependency pending | 2026-04-28 | M015 | Integration
2026-04-17 | Blocked | Issue investigation | 2026-04-17 | M038 | Deployment
2026-03-30 | Completed | Deployment prep | 2026-03-30 | M059 | Deployment
2026-04-18 | Not Started | Code review ongoing | 2026-04-18 | M076 | Requirement Signoff
2026-04-24 | On Hold | Initial development | 2026-04-24 | M017 | Core Features
2026-03-06 | In Progress | Client feedback applied | 2026-03-06 | M040 | Integration
2026-03-17 | On Hold | Issue investigation | 2026-03-17 | M061 | Testing
2026-03-30 | Blocked | Dependency pending | 2026-03-30 | M077 | Deployment
2026-04-07 | In Progress | Initial development | 2026-04-07 | M019 | Core Features
2026-03-07 | Not Started | Testing ongoing | 2026-03-07 | M042 | Deployment
2026-03-02 | On Hold | Initial development | 2026-03-02 | M063 | Final Delivery
2026-04-28 | On Hold | Task completed | 2026-04-28 | M078 | Deployment
2026-04-11 | Completed | Testing ongoing | 2026-04-11 | M021 | Requirement Signoff
2026-04-28 | Blocked | Code review ongoing | 2026-04-28 | M044 | Requirement Signoff
2026-03-08 | Not Started | Client feedback applied | 2026-03-08 | M065 | Final Delivery
2026-04-30 | Completed | Dependency pending | 2026-04-30 | M002 | Requirement Signoff
2026-04-01 | Completed | Issue investigation | 2026-04-01 | M023 | Requirement Signoff
2026-03-16 | On Hold | Deployment prep | 2026-03-16 | M046 | Requirement Signoff
2026-03-25 | In Progress | Initial development | 2026-03-25 | M067 | Deployment
2026-04-12 | On Hold | Code review ongoing | 2026-04-12 | M004 | Core Features
2026-04-07 | Not Started | Code review ongoing | 2026-04-07 | M025 | Core Features
2026-04-11 | Completed | Testing ongoing | 2026-04-11 | M048 | Testing
2026-04-09 | In Progress | Dependency pending | 2026-04-09 | M069 | Requirement Signoff
2026-03-03 | Blocked | Task completed | 2026-03-03 | M006 | Requirement Signoff
2026-03-29 | In Progress | Task completed | 2026-03-29 | M027 | Deployment
2026-04-24 | Blocked | Issue investigation | 2026-04-24 | M050 | Deployment
2026-04-13 | Blocked | Initial development | 2026-04-13 | M071 | Final Delivery
2026-03-04 | In Progress | Dependency pending | 2026-03-04 | M008 | Requirement Signoff
2026-03-13 | Completed | Testing ongoing | 2026-03-13 | M029 | Deployment
2026-03-06 | Not Started | Client feedback applied | 2026-03-06 | M052 | Deployment
2026-03-04 | Blocked | Task completed | 2026-03-04 | M072 | Testing
2026-03-09 | On Hold | Task completed | 2026-03-09 | M010 | Testing
2026-03-05 | On Hold | Task completed | 2026-03-05 | M031 | Deployment
2026-04-07 | Not Started | Task completed | 2026-04-07 | M054 | Final Delivery
2026-03-22 | Not Started | Client feedback applied | 2026-03-22 | M073 | Core Features
2026-03-18 | Not Started | Deployment prep | 2026-03-18 | M012 | Core Features
2026-04-04 | Blocked | Deployment prep | 2026-04-04 | M033 | Core Features
2026-03-08 | Completed | Deployment prep | 2026-03-08 | M056 | Integration
2026-03-01 | Blocked | Task completed | 2026-03-01 | M074 | Requirement Signoff
2026-04-07 | Blocked | Client feedback applied | 2026-04-07 | M014 | Deployment
2026-03-12 | Blocked | Client feedback applied | 2026-03-12 | M035 | Core Features
2026-03-09 | In Progress | Issue investigation | 2026-03-09 | M058 | Final Delivery
2026-04-17 | Completed | Testing ongoing | 2026-04-17 | M075 | Testing
2026-03-29 | Blocked | Issue investigation | 2026-03-29 | M016 | Integration
2026-03-29 | On Hold | Task completed | 2026-03-29 | M037 | Deployment
2026-04-30 | On Hold | Client feedback applied | 2026-04-30 | M060 | Deployment
2026-04-16 | On Hold | Dependency pending | 2026-04-16 | M076 | Requirement Signoff
2026-03-30 | Completed | Client feedback applied | 2026-03-30 | M018 | Core Features
2026-03-31 | In Progress | Code review ongoing | 2026-03-31 | M039 | Integration
2026-04-13 | Completed | Testing ongoing | 2026-04-13 | M062 | Testing
2026-04-15 | In Progress | Issue investigation | 2026-04-15 | M077 | Deployment
2026-04-27 | Completed | Initial development | 2026-04-27 | M020 | Core Features
2026-04-08 | Not Started | Issue investigation | 2026-04-08 | M041 | Deployment
2026-03-09 | Blocked | Initial development | 2026-03-09 | M064 | Final Delivery
2026-03-25 | On Hold | Dependency pending | 2026-03-25 | M078 | Deployment
2026-03-30 | On Hold | Code review ongoing | 2026-03-30 | M022 | Requirement Signoff
2026-03-07 | Completed | Task completed | 2026-03-07 | M043 | Requirement Signoff
2026-03-28 | In Progress | Task completed | 2026-03-28 | M066 | Final Delivery